## BCF
Financial Analysis for MediCare
Created by: Matteo Cicalese, Luca Contrasto |  | Date: | 2023-10-29
Discount rate | 8%
Assume the project is completed in 3 months |  |  | Year
| 0 | 1 | 2 | 3 | Total
Costs | 135000 | 17200 | 9900 | 9900 | 172000
Project Managers (300 hours, 75€/h) | 45000
Staff (300 hours, 50€/h) | 90000 | 9000 | 9000 | 9000
Hosting (Aruba) |  | 900 | 900 | 900
Instagram Advertising (20€/day) |  | 7300
Total project costs (applied in year 0) | 135000
Discount factor | 1 | 0.93 | 0.86 | 0.79
Discounted costs | 135000 | 15996 | 8514 | 7821 | 167331
Benefits | 10000 | 79615 | 90996 | 113745
European benefits (PNRR) | 10000 | 10000 | 10000 | 10000
Discount factor | 1 | 0.93 | 0.86 | 0.79
| 10000 | 74041.95 | 78256.56 | 89858.55 | 252157.06
Discounted benefits
Discounted benefits - costs | -125000 | 58045.95 | 69742.56 | 82037.55 | 84826.06 | NPV
Cumulative benefits - costs | -125000 | -66954.05 | 2788.51 | 84826.06
ROI | 50.69%
Payback in Year 2